## Project Regulatory Process
Regulatory process Flow Chart for AI Project Construction (From Project Set-up, Plant construction to commercial production) |  |  | Update： 2020.01
Stages | Project Approval | Safety and Environment Impact assessment | Project Engineering Design | Plant Construction | Equipment Installation | Trial Production Application | Trial Production | Completion Acceptance | Safety production Permit and Commercial production
Description | To set up a project internally, if the company is a state-owned enterprise, it will need the approval of investment | Third party agency will be involved to draft the reports based on lab test, process, site, etc, then the report will be submit for approval by government | Usually dedicated engieering design company design the plant, give blueprint for the plant | the base and the building construction | Installation after pant construction | After the plant is ready, the company will apply for trial production, usually they could use water to run the process first for simulation | The company could do trial production within the valid date of trial production permit | Duringr trial production, related governments will do on-site check of safety, environment and occupational issues for final approcal | After everything finished, they could get the safety production permit for the commercial production.
Item and Related Authority Approval | Feasibility Study report; Investment Application By Provincial Development and Reform Commission or Provincial Economical and Information Technology Commission | Safety pre-assessment and Approval By Provincial Administration of Work Safety Environment Impact assessment report and approval By Provincial Environment Protection Bureau Pre-assessment of occupational hazard and Approval By Provincial Administration of Work Safety | Design Inspection of Safety Devise By Provincial Administration of Work Safety | Plant base and building Construction application and Approval By Local Construction Bureau | Equipment Installtion by Internal Project Team | Trial Production Application and Approval by Local Fire fighting station; Provincial Administration of Work Safety; Local Environment protection Bureau | Trial Production (trial production period could be extended until completion acceptance done) | Safety Acceptance By Provincial Administration of Work Safety Environment acceptance By Provincial Environment Protection Bureau Occupational Acceptance By Provincial Administration of Work Safety | Safety Production Permit By Provincial Administration of Work Safety Commercial production